## Sheet1
S No | ID | EJ1/EJ2 | Control | Details | Promised Date /Patch | Type | Updated Date | Status | Feedback
1 | F11311 | EJ2 | Treeview | EjsTreeView - NodeTemplate is Not Handling Context Item Enums Correctly | Feb 2 week | Fix |  | Pending
2 | 261028 | EJ1 | ContextMenu | Context menu auto-closes after open if using word wrapped columns | Feb 2 week | Fix | 2020-02-12 | Updated
3 | 263245 | EJ2 | Slider | A slider with binding works just once | 2020-02-05 | Fix | 2020-02-06 | Updated
4 | 262595 | EJ1 | AutoCOmplete | Autocomplete sensitivity | 2020-02-20 | Fix | 2020-02-20 | Updated | https://www.syncfusion.com/feedback/11624/same-item-is-selected-twice-on-double-click-with-multiselect-mode
5 | 264330 | EJ1 | DropDownList | DropDownList not working as expected | 2020-02-25 | Validation | 2020-02-24 | Updated
6 | 261830 | EJ1 | Common - Grid | Freeze Filter selection | 2020-02-25 | Validation | 2020-02-25 | Updated
7 | 266148 | EJ1 | RTE | Font Property Issue in RTE Tool | 2020-02-28 | Fix | 2020-02-28 | Updated
8 | 266699 | EJ1 | common | Unable to start ASP.Net MVC webapp after adding nuget package syncfusion.aspnet.mvc5 | 2020-02-26 | Validation | 2020-02-26 | Updated
9 | 263939 | EJ1 | Listbox | ejListBox reset data source and enableIncrementalSearch | 2020-02-21 | Fix |  |  | https://www.syncfusion.com/feedback/12058/listbox-enableincrementalsearch-is-not-working-with-angular
10 | 267451 | EJ1 | DropDownList | DropDownList Selection Not Working Correctly When Virtual Scrolling Enabled | 2020-03-13 | Fix | 2020-03-16 | Updated
11 | 264330 | EJ1 | DropDownList | DropDownList not working as expected | 2020-03-13 | Fix | 2020-03-16 | Updated
12 | 152199 | EJ2 | Treeview | Drag drop of multiple nodes only shows one node in args | Vol 1 | Fix | 2020-04-06 | Updated
13 | 152235 | EJ1 | RadioButton | RadioButtonFor with boolean | 2020-03-25 | Fix
14 | 267451 | EJ1 | Dropdownlist | DropDownList Selection Not Working Correctly When Virtual Scrolling Enabled | 2020-03-18 | Fix | 2020-03-16 | Updated
15 | 269285 | EJ1 | Listbox | List box doesn't show 'false' string | 2020-03-24 | Fix | 2020-03-24 | Updated
16 | 269813 | EJ1 | FileExplorer | FileExplorer in BootStrap 3 Modal | 2020-04-09 | bug | 2020-04-09 | Updated
17 | 270365 | EJ1 | uploadbox | How to set hiddenfield value from 'ClientSideOnSuccess' or 'ClientSideOnComplete' | SP1 | feature
18 | 271567 | EJ1 | ThemeSTudio | js1 Theme Studio - download problem | SP1 | bug
19 | 269689 | EJ1 | Combobox | Binding issue while selecting item using auto complete option ej-comboBox (Autocomplete) | 2020-04-20 | bug | 2020-04-20 | updated
20 | 270390 | EJ1 | Menu | ejMenu - Resize bug when I hide an item | SP1 | feature
21 | 271382 | EJ1 | RTE | ejRte - Imagebrowser | 2020-04-21 | bug | 2020-04-21 | updated
22 | 272777 | EJ1 | AutoCOmplete | Autocomplete blur element and result open | SP1 | bug
23 | 272765 | EJ1 | AutoCOmplete | Autocomplete remote delete issue | SP1 | bug
24 | 272566 | EJ1 | Datepicker | DatePickerFor Problem | Vol 2 | bug
25 | 273828 | EJ1 | ThemeSTudio | Feedback : Feedback Page. | 2020-04-30 | bug