## Sheet1
ID | EJ1/EJ2 | Control | Details | Promised Date /Patch | Type | Updated Date | Status
F11311 | EJ2 | Treeview | EjsTreeView - NodeTemplate is Not Handling Context Item Enums Correctly | Feb 2 week | Fix |  | Pending
261028 | EJ1 | ContextMenu | Context menu auto-closes after open if using word wrapped columns | Feb 2 week | Fix | 2020-02-12 | Updated
263245 | EJ2 | Slider | A slider with binding works just once | 2020-02-05 | Fix | 2020-02-06 | Updated
262595 | EJ1 | AutoCOmplete | Autocomplete sensitivity | 2020-02-20 | Fix | 2020-02-20 | Updated
264330 | EJ1 | DropDownList | DropDownList not working as expected | 2020-02-25 | Validation | 2020-02-24 | Updated | Mailed to thiru
261830 | EJ1 | Common - Grid | Freeze Filter selection | 2020-02-25 | Validation | 2020-02-25 | Updated | Mailed to thiru
266148 | ej1 | RTE | Font Property Issue in RTE Tool | 2020-02-28 | Fix | 2020-02-28 | Updated | Mailed to thiru
266699 | ej1 | common | Unable to start ASP.Net MVC webapp after adding nuget package syncfusion.aspnet.mvc5 | 2020-02-26 | Validation | 2020-02-26 | Updated
263939 | ej1 | Listbox | ejListBox reset data source and enableIncrementalSearch | beta 1 | Fix
267451 | EJ1 | DropDownList | DropDownList Selection Not Working Correctly When Virtual Scrolling Enabled | 2020-03-13 | Fix | 2020-03-16 | Updated
264330 | EJ1 | DropDownList | DropDownList not working as expected | 2020-03-13 | Fix | 2020-03-16 | Updated
152199 | EJ2 | Treeview | Drag drop of multiple nodes only shows one node in args | Vol 1 | Fix
152235 | EJ1 | RadioButton | RadioButtonFor with boolean | 2020-03-25 | Fix
267451 | EJ1 | Dropdownlist | DropDownList Selection Not Working Correctly When Virtual Scrolling Enabled | 2020-03-18 | Fix | 2020-03-16 | Updated
269285 | EJ1 | Listbox | List box doesn't show 'false' string | 2020-03-24 | Fix
269813 | EJ1 | FileExplorer | FileExplorer in BootStrap 3 Modal | 2020-04-09